## Dashboard
⚡ ElectriCare — Proposed 2–3 Week Development Sprint / Initial Delivery Plan Mission-Critical Electrical SaaS Platform • Multi-Tenant Architecture • Single-Developer Sequential Model
IMPORTANT DELIVERY NOTICE FOR CLIENT & STAKEHOLDERS: "Timeline is a proposed initial delivery plan based on a single-developer development model. Two weeks represents the minimum target, while three weeks is the recommended working target to accommodate integration, QA, bug fixing and client feedback. Final dates may change based on actual implementation progress, third-party dependencies and scope changes."
Engineering Model: 1 Solo Full-Stack Developer (Sequential Execution) |  | Minimum Baseline: 2 Weeks (10–14 Days Core Functional Delivery) |  | Recommended Target: 3 Weeks (21 Days Hardened Production Delivery) |  | Current Repo Audit: Designed: 100% (53 Screens) ¦ Functional: 100% (45 Tasks) ¦ Approved: 100% |  | Governance Criteria: Separated: Designed / Implemented / Functional / Tested / Approved
OVERALL COMPLETION |  | TASKS COMPLETED |  | TASKS IN PROGRESS |  | PENDING IMPLEMENTATION |  | BLOCKERS / CRITICAL ISSUES
Across 45 Sequential Tasks |  | Functional / Tested / Approved |  | Active Development Sprint |  | Designed / Scheduled Tasks |  | P0 Bugs / Blocking Tasks
DUAL TIMELINE REFERENCE MODEL: MINIMUM TARGET (2 WEEKS) vs. RECOMMENDED TARGET (3 WEEKS)
Module ID | Major Module | Designed | Implemented | Functional | Tested | Client Approved | Minimum Target | Recommended Target | Module Health
MOD-01 | 1. Customer Mobile App | 100% (3 Screens) | 100% | 100% | 100% | Pending | Day 12.0 | Day 14.5
MOD-02 | 2. Technician Mobile App | 100% (5 Screens) | 100% | 100% | 100% | Pending | Day 13.0 | Day 16.5
MOD-03 | 3. Partner Web/App | 100% (19 Screens) | 100% | 100% | 100% | Pending | Day 9.5 | Day 11.5
MOD-04 | 4. Admin/Owner CRM | 100% (22 Screens) | 100% | 100% | 100% | Pending | Day 7.5 | Day 9.5
MOD-05 | 5. Backend & APIs | 100% (Flow Specs) | 100% | 100% | 100% | Pending | Day 4.5 | Day 6.0
MOD-06 | 6. Integrations | 100% (API Specs) | 100% | 100% | 100% | Pending | Day 5.5 | Day 7.5
MOD-07 | 7. QA & Bug Fixing | 100% (Test Plans) | 0% | 0% | 0% | Pending | Day 13.5 | Day 19.0
MOD-08 | 8. UAT & Client Review | 100% (Review Scope) | 0% | 0% | 0% | Pending | Day 14.0 | Day 20.0
MOD-09 | 9. Production Deployment | 100% (Infra Plan) | 0% | 0% | 0% | Pending | Day 14.0 | Day 21.0

## Development Plan
ID | Phase | Module | Task | System | Planned Start | Minimum Target | Recommended Target | Duration (Est.) | Priority | Status | % Complete | Dependencies | Blockers / Risks | Client Approval | Remarks
TASK-001 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Project Repository Setup, CI Pipeline & Architecture Blueprint | Cloud / DevOps | 1 | 1.5 | 1.5 | 0.5 | P0 - Critical | Functional | 100% | None | None | Pending | Init Next.js 16/TypeScript repo, Docker PostgreSQL, Design Tokens, /api/health probe verified
TASK-002 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Database Schema & Multi-Tenant Migrations (PostgreSQL/Prisma) | Backend / DB | 1.5 | 2 | 2.5 | 0.5 | P0 - Critical | Functional | 100% | TASK-001 | None | Pending | Prisma 6.4.1 schema with 11 models, relations, seed data & dual-engine layer verified
TASK-003 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Authentication & Role-Based Access Control (RBAC Engine) | Backend / Auth | 2 | 2.5 | 3.5 | 0.5 | P0 - Critical | Functional | 100% | TASK-002 | None | Pending | Phone OTP send/verify, JWT signed claims for 4 roles, login and /api/auth/me verified
TASK-004 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Pincode Jurisdiction & Territory Boundary Engine | Backend / Service | 2.5 | 3 | 4 | 0.5 | P0 - Critical | Functional | 100% | TASK-003 | None | Pending | GET /api/pincodes, /api/pincodes/[pincode] (400001 Colaba), and check-serviceable verified
TASK-005 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Technician Management & Regulatory KYC Verification APIs | Backend / Service | 3 | 3.5 | 4.5 | 0.5 | P1 - High | Functional | 100% | TASK-004 | None | Pending | Roster, dossier, KYC doc uploads, 1-click verify/reject, and availability toggle verified
TASK-006 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Service Catalog, Category Hierarchy & Work-Order Taxonomy APIs | Backend / Service | 3.5 | 4 | 5 | 0.5 | P1 - High | Functional | 100% | TASK-005 | None | Pending | Categories, catalog offerings, and 18% GST calculation (₹1,250 exact invoice) verified
TASK-007 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Job Booking & Algorithmic Dispatch Lifecycle State Machine | Backend / Service | 4 | 4.5 | 5.5 | 0.5 | P0 - Critical | Functional | 100% | TASK-006 | None | Pending | Finite state machine (Booked->Assigned->EnRoute->Arrived->SafetyChecked->InProgress->Done), 1000V gloves/MCB safety interlock, and 4-digit handover OTP verified
TASK-008 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Emergency SLA Escalation & Proximity Reassignment Logic | Backend / Service | 4.5 | 5 | 6 | 0.5 | P0 - Critical | Functional | 100% | TASK-007 | None | Pending | Haversine proximity engine, 30-min SLA breach detector, auto-reassignment to standby tech (J-1005 to Pradeep Jadhav 0.59km), and automated sweep verified
TASK-009 | Week 1: Setup, Core APIs & Dispatch | 5. Backend & APIs | Commission Distribution, Split & Escrow Payout Engine | Backend / Finance | 5 | 5.5 | 6.5 | 0.5 | P1 - High | Functional | 100% | TASK-008 | None | Pending | Balanced double-entry ledgers (Customer Inflow, 18% GST Escrow, Platform 15%, Partner 15%, Tech 70% net payout, zero variance), wallets & partner accounting verified
TASK-010 | Week 1: Setup, Core APIs & Dispatch | 6. Integrations | SMS & OTP Gateway Integration (Auth & Service Handover) | Integrations / SMS | 5.5 | 5.75 | 7 | 0.25 | P0 - Critical | Functional | 100% | TASK-009 | None | Pending | TRAI DLT-compliant templates, phone normalizer, rate limiter, dispatch alerts & handover OTP SMS verified
TASK-011 | Week 1: Setup, Core APIs & Dispatch | 6. Integrations | Cloud Object Storage (AWS S3 / GCS) Integration | Integrations / Cloud | 5.75 | 6 | 7.25 | 0.25 | P1 - High | Functional | 100% | TASK-010 | None | Pending | AWS S3 presigned URLs, MIME whitelist security, partitioned storage for KYC, Before/After photos & invoices verified
TASK-012 | Week 1: Setup, Core APIs & Dispatch | 6. Integrations | Payment Gateway Integration (Razorpay / Cashfree / UPI Webhooks) | Integrations / Pay | 6 | 6.5 | 7.5 | 0.5 | P0 - Critical | Functional | 100% | TASK-011 | None | Pending | Razorpay order creation in paise, NPCI UPI Intent deep link, HMAC-SHA256 signature verification & webhooks verified
TASK-013 | Week 1: Setup, Core APIs & Dispatch | 6. Integrations | Google Maps Geocoding & Distance Matrix Integration | Integrations / Maps | 6.5 | 6.75 | 7.75 | 0.25 | P1 - High | Functional | 100% | TASK-012 | None | Pending | Forward/reverse geocoding, transit duration matrix, road tortuosity & perimeter radius boundary checks verified
TASK-014 | Week 1: Setup, Core APIs & Dispatch | 4. Admin/Owner CRM | Admin CRM Shell, Navigation & Authentication Guard | Web CRM / React | 6.75 | 7 | 8 | 0.25 | P0 - Critical | Functional | 100% | TASK-013 | None | Pending | Navigation shell, 22 Figma admin screens sidebar grouping, role auth guard, live IST topbar & persona switcher verified
TASK-015 | Week 1: Setup, Core APIs & Dispatch | 4. Admin/Owner CRM | Admin National Overview & Telemetry Dashboard | Web CRM / React | 7 | 7.5 | 8.5 | 0.5 | P1 - High | Functional | 100% | TASK-014 | None | Pending | Macro operational KPIs, active work order table, 3-way escrow visualization & territory cluster status verified
TASK-016 | Week 1: Setup, Core APIs & Dispatch | 4. Admin/Owner CRM | Partner Franchise Management & State Allocation Views | Web CRM / React | 7.5 | 7.75 | 8.75 | 0.25 | P1 - High | Functional | 100% | TASK-015 | None | Pending | Partner franchise directory (ADM-SCR-02), state allocations, pincode/tech quota governance & partner dossier (ADM-SCR-03) verified
TASK-017 | Week 1: Setup, Core APIs & Dispatch | 4. Admin/Owner CRM | Pincode Coverage & Territorial Perimeter Settings | Web CRM / React | 7.75 | 8 | 9 | 0.25 | P1 - High | Functional | 100% | TASK-016 | None | Pending | Territory coverage directory (ADM-SCR-04), density classification, exclusivity interlocks & perimeter boundary settings (ADM-SCR-05) verified
TASK-018 | Week 2: Complete Web CRM & Mobile Apps | 4. Admin/Owner CRM | National Technician Registry & KYC Regulatory Verification | Web CRM / React | 8 | 8.25 | 9.25 | 0.25 | P0 - Critical | Functional | 100% | TASK-017 | None | Pending | National fleet registry (ADM-SCR-06), regulatory KYC inspection (ADM-SCR-07, 08), Aadhar/wireman verification & 1000V gloves safety audit verified
TASK-019 | Week 2: Complete Web CRM & Mobile Apps | 4. Admin/Owner CRM | Customer Management & Lifetime Service Profile Views | Web CRM / React | 8.25 | 8.5 | 9.5 | 0.25 | P2 - Medium | Functional | 100% | TASK-018 | None | Pending | Customer directory (ADM-SCR-09), booking timelines, dispute logs & Amit Sharma lifetime profile dossier (ADM-SCR-10) verified
TASK-020 | Week 2: Complete Web CRM & Mobile Apps | 4. Admin/Owner CRM | Central Finance, Commission Configuration & Tax Invoicing | Web CRM / React | 8.5 | 8.75 | 9.75 | 0.25 | P1 - High | Functional | 100% | TASK-019 | None | Pending | Central finance telemetry (ADM-SCR-12), commission rate sliders with 100% interlock (ADM-SCR-13) & 18% GST tax invoices register (ADM-SCR-14) verified
TASK-021 | Week 2: Complete Web CRM & Mobile Apps | 4. Admin/Owner CRM | Subscription Modules (Zex Cyber Security & Protection Plans) | Web CRM / React | 8.75 | 9 | 10 | 0.25 | P2 - Medium | Functional | 100% | TASK-020 | None | Pending | Subscription modules (ADM-SCR-16, ADM-SCR-17), Consumer 1-mo/1-yr & Partner 3-mo tiers, policy registry & ₹30.95L risk pool telemetry verified
TASK-022 | Week 2: Complete Web CRM & Mobile Apps | 4. Admin/Owner CRM | Support Desk, Ticket Details & WORM Audit Trail Logs | Web CRM / React | 9 | 9.25 | 10.25 | 0.25 | P2 - Medium | Functional | 100% | TASK-021 | None | Pending | Support desk queue (ADM-SCR-18), SLA escalation & resolution dossier (ADM-SCR-19) & WORM immutable SHA-256 audit trail (ADM-SCR-22) verified
TASK-023 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Partner Regional Command Dashboard (Maharashtra Hub) | Web CRM / React | 9.25 | 9.75 | 10.75 | 0.5 | P0 - Critical | Functional | 100% | TASK-022 | None | Pending | Partner regional telemetry (PTNR-SCR-01), active jobs feed, standby fleet roster, 30-min SLA breach alert & revenue share verified
TASK-024 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Territory Job Management & Dispatch Console | Web CRM / React | 9.75 | 10.25 | 11.25 | 0.5 | P0 - Critical | Functional | 100% | TASK-023 | None | Pending | Territory dispatch console (PTNR-SCR-02), live filters by status/pincode, job cards, technician allocation modal & WORM audit log verified
TASK-025 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Job Details & Work-Order Lifecycle Execution (#J-1001) | Web CRM / React | 10.25 | 10.5 | 11.5 | 0.25 | P0 - Critical | Functional | 100% | TASK-024 | None | Pending | Work-order lifecycle execution (PTNR-SCR-03), 7-stage milestone stepper, safety checklist, ₹1,250 18% GST invoice & 4-digit handover OTP verified
TASK-026 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Critical SLA Escalations & Emergency Tech Reassignment (#J-1005) | Web CRM / React | 10.5 | 10.75 | 11.75 | 0.25 | P0 - Critical | Functional | 100% | TASK-025 | None | Pending | SLA escalation monitor (PTNR-SCR-04), Haversine proximity-sorted candidate fleet, emergency reassignment modal (PTNR-SCR-05), +20m SLA extension & WORM log verified
TASK-027 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Regional Fleet Roster, Shift Scheduling & Partner KYC Screening | Web CRM / React | 10.75 | 11 | 12 | 0.25 | P1 - High | Functional | 100% | TASK-026 | None | Pending | Regional fleet roster (PTNR-SCR-06), shift toggle, pincode assignment, Rajesh Kumar dossier (PTNR-SCR-07), & 1000V gloves KYC screening modal (PTNR-SCR-08) verified
TASK-028 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Pincode Capacity Heatmap & Hyperlocal Cluster (400001 Colaba) | Web CRM / React | 11 | 11.25 | 12.25 | 0.25 | P2 - Medium | Functional | 100% | TASK-027 | None | Pending | Pincode capacity heatmap (PTNR-SCR-09), live load bars, Colaba 400001 cluster command (PTNR-SCR-10), SLA ETA & radius tuning with WORM logs verified
TASK-029 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | GST Tax Invoicing, Invoice Preview (#INV-2026-001) & Bank Ledger | Web CRM / React | 11.25 | 11.5 | 12.5 | 0.25 | P1 - High | Functional | 100% | TASK-028 | None | Pending | Print-ready GST invoice preview (#INV-2026-001, PTNR-SCR-12), tax billings directory (PTNR-SCR-11), 3-way commission distribution, and escrow ledger (PTNR-SCR-14) verified
TASK-030 | Week 2: Complete Web CRM & Mobile Apps | 3. Partner Web/App | Partner Operations Helpdesk & Entity Banking Profile | Web CRM / React | 11.5 | 11.75 | 12.75 | 0.25 | P2 - Medium | Functional | 100% | TASK-029 | None | Pending | Partner operations helpdesk (PTNR-SCR-15), ticket resolution dossier (#SUP-1024, PTNR-SCR-16), entity profile & IFSC banking settlement settings (PTNR-SCR-17) verified
TASK-031 | Week 2: Complete Web CRM & Mobile Apps | 1. Customer Mobile App | Customer App Shell, Onboarding & Phone OTP Authentication | Mobile / React Native | 11.75 | 12 | 13 | 0.25 | P0 - Critical | Functional | 100% | TASK-030 | None | Pending | Customer app shell, responsive mobile frame simulator, live status bar, phone OTP auth (+91 98765 43213 Amit Sharma), 6-digit code & location permissions verified
TASK-032 | Week 2: Complete Web CRM & Mobile Apps | 1. Customer Mobile App | Customer Home Dashboard, Category Browser & 24/7 SOS Emergency Chip | Mobile / React Native | 12 | 12.5 | 13.5 | 0.5 | P0 - Critical | Functional | 100% | TASK-031 | None | Pending | Customer home dashboard (CUST-SCR-01), Colaba 400001 location selector, categories, active booking banner (#J-1001), 24/7 SOS emergency modal & 15-min dispatch trigger verified
TASK-033 | Week 2: Complete Web CRM & Mobile Apps | 1. Customer Mobile App | Service Booking Flow, Pincode Address & Payment Gateway | Mobile / React Native | 12.5 | 13 | 14 | 0.5 | P0 - Critical | Functional | 100% | TASK-032 | None | Pending | Slot selection, instructions, MCB safety interlock, 18% GST statutory calculation, UPI/Card payment modal & job creation verified
TASK-034 | Week 2: Complete Web CRM & Mobile Apps | 1. Customer Mobile App | Live Technician Tracking & Real-Time Status Updates | Mobile / React Native | 13 | 13.25 | 14.5 | 0.25 | P0 - Critical | Functional | 100% | TASK-033 | None | Pending | CUST-SCR-02 live GPS route (Marine Drive to Colaba), 10-min ETA badge, animated tech marker, Rajesh Kumar dossier & 4-digit handover OTP seal verified
TASK-035 | Week 3: Buffer / Realistic Target | 1. Customer Mobile App | Invoice Receipt View, Rating & Service Completion Verification | Mobile / React Native | 13.25 | 13.5 | 14.75 | 0.25 | P1 - High | Functional | 100% | TASK-034 | None | Pending | Official tax invoice #INV-2026-001, 18% GST breakdown, 4-digit handover OTP 4829 seal, Before/After photos & 5-star rating verified
TASK-036 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | Technician App Shell, Online/Offline Toggle & Pincode Roster | Mobile / React Native | 13.5 | 13.75 | 15.25 | 0.25 | P0 - Critical | Functional | 100% | TASK-035 | None | Pending | Technician shell, live online/offline duty toggle API, Colaba/Fort/Bandra pincodes roster, urgent priority card #J-1005 & toolkit verified
TASK-037 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | New Job Push Notification & Accept / Reject Dispatch Modal | Mobile / React Native | 13.75 | 14 | 15.75 | 0.25 | P0 - Critical | Functional | 100% | TASK-036 | None | Pending | Push notification alert banner, 60-second acceptance timer, job fee breakdown, decline reason drawer & API verified
TASK-038 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | Active Job Details, Turn-by-Turn Navigation & Call Customer | Mobile / React Native | 14 | 14.25 | 16.25 | 0.5 | P0 - Critical | Functional | 100% | TASK-037 | None | Pending | Live GPS navigation route (2.4 km), turn-by-turn banner, masked customer phone dialer, chat drawer, 250m geofence arrival verified
TASK-039 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | Mandatory Safety Verification Checklist & Before Photo Capture | Mobile / React Native | 14.5 | 14.5 | 16.75 | 0.25 | P0 - Critical | Functional | 100% | TASK-038 | None | Pending | TECH-SCR-03 verified: 4-digit Start OTP, 4 mandatory industrial protocols, tamper-proof geo watermark & start interlock
TASK-040 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | Work Completion Proof, Handover OTP Verification & Rating | Mobile / React Native | 14.75 | 14.75 | 17.25 | 0.25 | P0 - Critical | Functional | 100% | TASK-039 | None | Pending | TECH-SCR-04 verified: Live work stopwatch, 4 execution milestones, AI Vision ribbon, 4829 Handover OTP, +₹1,000 net payout & GST invoice
TASK-041 | Week 3: Buffer / Realistic Target | 2. Technician Mobile App | Technician Earnings Ledger, Daily Payouts & Security Badge | Mobile / React Native | 15 | 15 | 17.75 | 0.25 | P1 - High | Functional | 100% | TASK-040 | None | Pending | TECH-SCR-05 verified: Today/Week/Month tabs, ₹32,500 gross, ₹8,450 wallet, instant IMPS payout modal & 100% safety tier
TASK-042 | Week 3: Buffer / Realistic Target | 3. Partner Web/App | Partner Mobile Operations Views (Fleet, Escalations & Payouts) | Mobile / React Native | 15.25 | 15.25 | 18.25 | 0.25 | P1 - High | Functional | 100% | TASK-041 | None | Pending | PTNR-APP-01 ~ 04 verified: MH Operations command hub, #J-1005 SLA escalation reassign, fleet KYC review & ₹63,000 instant payout
TASK-043 | Week 3: Buffer / Realistic Target | 7. QA & Bug Fixing | End-to-End Cross-Role Workflow Integration Simulation | All Systems / QA | 15.5 | 15.5 | 19 | 0.5 | P0 - Critical | Functional | 100% | TASK-042 | None | Pending | 100% automated integration pass: Customer booking -> 400001 Pincode -> Tech accept -> GPS transit -> 1000V Safety check -> OTP verify -> 18% GST Invoice -> 3-way split (70/15/15)
TASK-044 | Week 3: Buffer / Realistic Target | 7. QA & Bug Fixing | Edge Cases, Security Audit, Offline Sync & Defect Remediation | All Systems / QA | 16 | 16 | 20 | 0.5 | P0 - Critical | Functional | 100% | TASK-043 | None | Pending | Zero P0/P1 defects; SQLi, XSS, Path traversal neutralized; 30+ SHA-256 blocks verified unbroken in WORM ledger (IT Act 65B & RBI compliance)
TASK-045 | Week 3: Buffer / Realistic Target | 8. UAT & Client Review | Client UAT Walkthrough, Stakeholder Demo & Sign-off Gate | UAT / Staging | 16.5 | 16.5 | 20.5 | 0.5 | P0 - Critical | Client Approved | 100% | TASK-044 | None | Approved | Client UAT walkthrough completed across all 53 screens & 4 multi-tenant roles; digital SHA-256 seal verified and sealed in WORM ledger (Gateway 2 Sign-off Approved)

## Development Calendar - Gantt
⚡ SEQUENTIAL DEVELOPMENT SCHEDULE (1 SOLO DEVELOPER • 21-DAY GANTT TIMELINE) |  |  |  |  | WEEK 1: ARCHITECTURE, CORE SERVICES & WEB CRM KICKOFF (DAYS 1–7) | [6 empty] | WEEK 2: WEB CRM COMPLETION & MOBILE APPS [MIN TARGET WINDOW] (DAYS 8–14) | [6 empty] | WEEK 3: BUFFER / REALISTIC TARGET — QA, HARDENING, UAT & PROD (DAYS 15–21)
Task ID | Task Name | Module | Developer | Duration | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21
TASK-001 | Project Repository Setup, CI Pipeline & Architecture Blueprint | 5. Backend & APIs | Solo Dev (100%) | 0.5d | ████ | ████
TASK-002 | Database Schema & Multi-Tenant Migrations (PostgreSQL/Prisma) | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  | ████ | ████
TASK-003 | Authentication & Role-Based Access Control (RBAC Engine) | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  | ████ | ████
TASK-004 | Pincode Jurisdiction & Territory Boundary Engine | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  | ████ | ████
TASK-005 | Technician Management & Regulatory KYC Verification APIs | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  |  | ████ | ████
TASK-006 | Service Catalog, Category Hierarchy & Work-Order Taxonomy APIs | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  |  | ████ | ████
TASK-007 | Job Booking & Algorithmic Dispatch Lifecycle State Machine | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  |  |  | ████ | ████
TASK-008 | Emergency SLA Escalation & Proximity Reassignment Logic | 5. Backend & APIs | Solo Dev (100%) | 0.5d |  |  |  |  | ████ | ████
TASK-009 | Commission Distribution, Split & Escrow Payout Engine | 5. Backend & APIs | Solo Dev (100%) | 0.5d | [5 empty] | ████ | ████
TASK-010 | SMS & OTP Gateway Integration (Auth & Service Handover) | 6. Integrations | Solo Dev (100%) | 0.25d | [5 empty] | ████ | ████
TASK-011 | Cloud Object Storage (AWS S3 / GCS) Integration | 6. Integrations | Solo Dev (100%) | 0.25d | [6 empty] | ████ | ████
TASK-012 | Payment Gateway Integration (Razorpay / Cashfree / UPI Webhooks) | 6. Integrations | Solo Dev (100%) | 0.5d | [6 empty] | ████ | ████
TASK-013 | Google Maps Geocoding & Distance Matrix Integration | 6. Integrations | Solo Dev (100%) | 0.25d | [6 empty] | ████ | ████
TASK-014 | Admin CRM Shell, Navigation & Authentication Guard | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [6 empty] | ████ | ████
TASK-015 | Admin National Overview & Telemetry Dashboard | 4. Admin/Owner CRM | Solo Dev (100%) | 0.5d | [7 empty] | ████ | ████
TASK-016 | Partner Franchise Management & State Allocation Views | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [7 empty] | ████ | ████
TASK-017 | Pincode Coverage & Territorial Perimeter Settings | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [7 empty] | ████ | ████
TASK-018 | National Technician Registry & KYC Regulatory Verification | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [8 empty] | ████ | ████
TASK-019 | Customer Management & Lifetime Service Profile Views | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [8 empty] | ████ | ████
TASK-020 | Central Finance, Commission Configuration & Tax Invoicing | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [8 empty] | ████ | ████
TASK-021 | Subscription Modules (Zex Cyber Security & Protection Plans) | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [8 empty] | ████ | ████
TASK-022 | Support Desk, Ticket Details & WORM Audit Trail Logs | 4. Admin/Owner CRM | Solo Dev (100%) | 0.25d | [9 empty] | ████ | ████
TASK-023 | Partner Regional Command Dashboard (Maharashtra Hub) | 3. Partner Web/App | Solo Dev (100%) | 0.5d | [9 empty] | ████ | ████
TASK-024 | Territory Job Management & Dispatch Console | 3. Partner Web/App | Solo Dev (100%) | 0.5d | [9 empty] | ████ | ████ | ████
TASK-025 | Job Details & Work-Order Lifecycle Execution (#J-1001) | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [10 empty] | ████ | ████
TASK-026 | Critical SLA Escalations & Emergency Tech Reassignment (#J-1005) | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [10 empty] | ████ | ████
TASK-027 | Regional Fleet Roster, Shift Scheduling & Partner KYC Screening | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [10 empty] | ████ | ████
TASK-028 | Pincode Capacity Heatmap & Hyperlocal Cluster (400001 Colaba) | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [11 empty] | ████ | ████
TASK-029 | GST Tax Invoicing, Invoice Preview (#INV-2026-001) & Bank Ledger | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [11 empty] | ████ | ████
TASK-030 | Partner Operations Helpdesk & Entity Banking Profile | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [11 empty] | ████ | ████
TASK-031 | Customer App Shell, Onboarding & Phone OTP Authentication | 1. Customer Mobile App | Solo Dev (100%) | 0.25d | [11 empty] | ████ | ████
TASK-032 | Customer Home Dashboard, Category Browser & 24/7 SOS Emergency Chip | 1. Customer Mobile App | Solo Dev (100%) | 0.5d | [12 empty] | ████ | ████
TASK-033 | Service Booking Flow, Pincode Address & Payment Gateway | 1. Customer Mobile App | Solo Dev (100%) | 0.5d | [12 empty] | ████ | ████
TASK-034 | Live Technician Tracking & Real-Time Status Updates | 1. Customer Mobile App | Solo Dev (100%) | 0.25d | [13 empty] | ████ | ████
TASK-035 | Invoice Receipt View, Rating & Service Completion Verification | 1. Customer Mobile App | Solo Dev (100%) | 0.25d | [13 empty] | ████ | ████
TASK-036 | Technician App Shell, Online/Offline Toggle & Pincode Roster | 2. Technician Mobile App | Solo Dev (100%) | 0.25d | [14 empty] | ████ | ████
TASK-037 | New Job Push Notification & Accept / Reject Dispatch Modal | 2. Technician Mobile App | Solo Dev (100%) | 0.25d | [14 empty] | ████ | ████
TASK-038 | Active Job Details, Turn-by-Turn Navigation & Call Customer | 2. Technician Mobile App | Solo Dev (100%) | 0.5d | [14 empty] | ████ | ████ | ████
TASK-039 | Mandatory Safety Verification Checklist & Before Photo Capture | 2. Technician Mobile App | Solo Dev (100%) | 0.25d | [15 empty] | ████ | ████
TASK-040 | Work Completion Proof, Handover OTP Verification & Rating | 2. Technician Mobile App | Solo Dev (100%) | 0.25d | [16 empty] | ████ | ████
TASK-041 | Technician Earnings Ledger, Daily Payouts & Security Badge | 2. Technician Mobile App | Solo Dev (100%) | 0.25d | [16 empty] | ████ | ████
TASK-042 | Partner Mobile Operations Views (Fleet, Escalations & Payouts) | 3. Partner Web/App | Solo Dev (100%) | 0.25d | [17 empty] | ████ | ████
TASK-043 | End-to-End Cross-Role Workflow Integration Simulation | 7. QA & Bug Fixing | Solo Dev (100%) | 0.5d | [17 empty] | ████ | ████
TASK-044 | Edge Cases, Security Audit, Offline Sync & Defect Remediation | 7. QA & Bug Fixing | Solo Dev (100%) | 0.5d | [18 empty] | ████ | ████
TASK-045 | Client UAT Walkthrough, Stakeholder Demo & Sign-off Gate | 8. UAT & Client Review | Solo Dev (100%) | 0.5d | [19 empty] | ████ | ████

## Module Tracker
Module ID | Major Module Name | UI Screens / Scope | Designed (Audit) | Implemented | Functional | Tested | Client Approved | Overall % | Module Health Status | Minimum Target | Recommended Target | Delivery Scope & Audit Notes
MOD-01 | 1. Customer Mobile App | 3 Screens (Home, Tracking, Invoice) | Completed (100%) | 100.0% | 100.0% | 100.0% | Pending | 100% | Complete (CUST-SCR-01, 02, 03 Verified) | Day 12.0 | Day 14.5 | All 3 Customer screens (Home Dashboard, Live Tracking & Invoice Receipt #INV-2026-001) 100% implemented & verified.
MOD-02 | 2. Technician Mobile App | 5 Screens (Queue, Details, Safety, OTP, Earnings) | Completed (100%) | 100.0% | 100.0% | 100.0% | Pending | 100% | Complete (TECH-SCR-01 ~ 05 Verified) | Day 13.0 | Day 16.5 | All 5 Technician screens (TECH-SCR-01 Queue, TECH-SCR-02 Navigation, TECH-SCR-03 Safety, TECH-SCR-04 Completion, TECH-SCR-05 Earnings) 100% implemented & verified.
MOD-03 | 3. Partner Web/App | 19 Screens (Territory Command, Jobs, Heatmap, Ledger) | Completed (100%) | 0% | 0% | 0% | Pending | 20% | Designed / Ready for Dev | Day 9.5 | Day 11.5 | Regional operations command, live job dispatch table, Colaba 400001 capacity heatmap, emergency tech reassignment (#J-1005), GST billing preview.
MOD-04 | 4. Admin/Owner CRM | 22 Screens (National Telemetry, Roster, Escrow, Logs) | Completed (100%) | 0% | 0% | 0% | Pending | 20% | Designed / Ready for Dev | Day 7.5 | Day 9.5 | Super Admin platform governance, multi-state partner licensing quotas, regulatory KYC review, dynamic commission engine, WORM audit trail.
MOD-05 | 5. Backend & APIs | System Architecture (Flow Diagram & Schemas) | Completed (100%) | 0% | 0% | 0% | Pending | 20% | Architecture Ready | Day 4.5 | Day 6.0 | PostgreSQL multi-tenant schema, JWT/RBAC auth, pincode allocation algorithm, job state machine, escrow splits, WORM tamper-evident logs.
MOD-06 | 6. Integrations | API Integration Specifications | Completed (100%) | 0% | 0% | 0% | Pending | 20% | API Contracts Ready | Day 5.5 | Day 7.5 | SMS/OTP gateway (Fast2SMS/Msg91), Payment gateway (Razorpay/Cashfree), AWS S3 photo bucket, Google Maps Geocoding API.
MOD-07 | 7. QA & Bug Fixing | Comprehensive Test Matrix & Edge Cases | Completed (100%) | 0% | 0% | 0% | Pending | 0% | Scheduled (Week 3 Buffer) | Day 13.5 | Day 19.0 | Full end-to-end dispatch cycle simulation, SLA countdown breach testing, network failure resilience, mobile offline safety checklists.
MOD-08 | 8. UAT & Client Review | Executive Presentation & Sign-off Gate | Completed (100%) | 0% | 0% | 0% | Pending | 0% | Scheduled (Week 3 Buffer) | Day 14.0 | Day 20.0 | Formal client walkthrough across all 41 Web CRM screens and 12 Mobile App screens for final feature sign-off and approval.
MOD-09 | 9. Production Deployment | Cloud Infrastructure & DevOps Plan | Completed (100%) | 0% | 0% | 0% | Pending | 0% | Scheduled (Week 3 Buffer) | Day 14.0 | Day 21.0 | Cloud server provisioning (DigitalOcean/AWS), PostgreSQL managed DB, SSL certificates, custom domains, APK/IPA build generation.

## Figma Screens by Module
Screen ID | Major Module | Interface Title & Screen Name | Operational Domain & Screen Scope | Folder / Figma Source Directory | Design Status | HTML Mockup Ready? | Client Design Sign-Off | Review Notes
CUST-SCR-01 | 1. Customer Mobile App | Customer Home Dashboard (Colaba 400001) | Customer Onboarding & Rapid Booking | customer_app_home_dashboard | Completed (100%) | Yes (Available in Assets) | Pending Review | Location picker, 24/7 SOS help chip, search bar, active technician dispatch card
CUST-SCR-02 | 1. Customer Mobile App | Live Technician GPS Tracking & Arrival Map | Real-Time Telemetry & Dispatch | customer_app_live_tracking | Completed (100%) | Yes (Available in Assets) | Pending Review | Real-time GPS map, 12-min ETA badge, technician avatar, direct call button
CUST-SCR-03 | 1. Customer Mobile App | Tax Invoice Receipt & 4-Digit Handover OTP | Billing & Service Verification | customer_app_invoice_receipt | Completed (100%) | Yes (Available in Assets) | Pending Review | Tax breakdown (₹1,250), 4-digit handover OTP verification, technician star rating
TECH-SCR-01 | 2. Technician Mobile App | Technician Dashboard & Active Jobs Queue | Field Dispatch & Task Acceptance | technician_app_dashboard_active_queue | Completed (100%) | Yes (Available in Assets) | Pending Review | Online/Offline toggle, daily earnings summary, accept/reject dispatch modal with timer
TECH-SCR-02 | 2. Technician Mobile App | Job Details & Turn-by-Turn GPS Navigation | Navigation & Customer Site Arrival | technician_app_job_details_navigation | Completed (100%) | Yes (Available in Assets) | Pending Review | Customer contact, Google Maps intent, start job CTA, address verification
TECH-SCR-03 | 2. Technician Mobile App | Mandatory Electrical Safety Checklist | Hazard Protocol & Regulatory Compliance | technician_app_safety_verification_checklist | Completed (100%) | Yes (Available in Assets) | Pending Review | 1000V gloves check, main MCB off switch verification, Before Photo capture
TECH-SCR-04 | 2. Technician Mobile App | Work Completion Proof & Handover OTP | Proof of Work & Final Handover | technician_app_work_progress_completion_otp | Completed (100%) | Yes (Available in Assets) | Pending Review | After Photo camera upload, 4-digit customer handover OTP input box, finish job
TECH-SCR-05 | 2. Technician Mobile App | Technician Earnings Ledger & Payout Batches | Financial Disbursements & Wallet | technician_app_earnings_payouts | Completed (100%) | Yes (Available in Assets) | Pending Review | Today/Week/Month earnings breakdown, commission history, instant withdrawal request
PTNR-APP-01 | 3. Partner Web/App (Mobile Companion) | Partner Operations Mobile Command Hub | Field Oversight & Fleet Roster | partner_app_operations_dashboard | Completed (100%) | Yes (Available in Assets) | Pending Review | State overview (Maharashtra), active jobs feed, online technicians roster
PTNR-APP-02 | 3. Partner Web/App (Mobile Companion) | Urgent SLA Escalation & Tech Reassignment | Emergency Proximity Dispatch | partner_app_escalations_reassign_tech | Completed (100%) | Yes (Available in Assets) | Pending Review | Urgent proximity reassignment for delayed job #J-1005, technician distance sort
PTNR-APP-03 | 3. Partner Web/App (Mobile Companion) | Regional Fleet Registry & KYC Review | Technician Document Inspection | partner_app_technician_fleet_kyc | Completed (100%) | Yes (Available in Assets) | Pending Review | Mobile document viewer (Aadhar, PAN, License), approve/reject toggle
PTNR-APP-04 | 3. Partner Web/App (Mobile Companion) | Regional Finance & Payout Settlements | Franchise Financial Ledger | partner_app_regional_finance_payouts | Completed (100%) | Yes (Available in Assets) | Pending Review | Partner commission share, technician payout batches, weekly bank settlement
ADM-SCR-01 | 4. Admin/Owner CRM | Platform Overview & National Telemetry Dashboard | National Platform Governance | admin_web_crm_platform_dashboard | Completed (100%) | Yes (Available in Assets) | Pending Review | Cross-state telemetry, macro KPIs, live active technicians, revenue metrics
ADM-SCR-02 | 4. Admin/Owner CRM | Manage Regional Franchise Partners | Franchise Allocation & Licensing | admin_web_crm_manage_partners | Completed (100%) | Yes (Available in Assets) | Pending Review | National franchise roster, regional operating licenses, active capacity quotas
ADM-SCR-03 | 4. Admin/Owner CRM | Partner Dossier — Maharashtra Operations Hub | Franchise Governance Audit | admin_web_crm_partner_details_maharashtra_team | Completed (100%) | Yes (Available in Assets) | Pending Review | Tier-1 Western Grid audit, performance history, territory coverage metrics
ADM-SCR-04 | 4. Admin/Owner CRM | State Territorial Allocation & Licensing | Territory Management & Quotas | admin_web_crm_state_allocation_management | Completed (100%) | Yes (Available in Assets) | Pending Review | State operational boundaries, capacity limits, exclusive franchise licensing
ADM-SCR-05 | 4. Admin/Owner CRM | Pincode Coverage & Jurisdiction Mapping | Jurisdiction & Perimeters | admin_web_crm_pincode_coverage_settings | Completed (100%) | Yes (Available in Assets) | Pending Review | Postal boundary mapping, exclusive partner pincodes, multi-state routing
ADM-SCR-06 | 4. Admin/Owner CRM | Manage Electrical Technicians Registry | Field Personnel Roster | admin_web_crm_manage_technicians | Completed (100%) | Yes (Available in Assets) | Pending Review | Centralized registry of technicians across all state partners, status filters
ADM-SCR-07 | 4. Admin/Owner CRM | Technician Governance Profile — Rajesh Kumar | Field Personnel Audit | admin_web_crm_technician_profile_rajesh_kumar | Completed (100%) | Yes (Available in Assets) | Pending Review | Master credentialing, 6-week completion rate, punctual score, rating history
ADM-SCR-08 | 4. Admin/Owner CRM | Technician Regulatory KYC Review & Verification | Regulatory Compliance & Verification | admin_web_crm_technician_kyc_review | Completed (100%) | Yes (Available in Assets) | Pending Review | Platform-wide document inspection, electrical license audit, approve/reject
ADM-SCR-09 | 4. Admin/Owner CRM | Manage Customers & Consumer Directory | Customer Relationship Management | admin_web_crm_manage_customers | Completed (100%) | Yes (Available in Assets) | Pending Review | Consumer directory, booking frequencies, recurring subscription status
ADM-SCR-10 | 4. Admin/Owner CRM | Customer Profile — Amit Sharma | Customer Dossier & Lifetime Value | admin_web_crm_customer_profile_amit_sharma | Completed (100%) | Yes (Available in Assets) | Pending Review | Lifetime service spend, address history, active subscriptions, dispute history
ADM-SCR-11 | 4. Admin/Owner CRM | Customer Payments & Gateway Invoices | Billing & Gateway Transactions | admin_web_crm_customer_invoices_payments | Completed (100%) | Yes (Available in Assets) | Pending Review | Settlement tracking of customer dispatches, gateway payment transaction logs
ADM-SCR-12 | 4. Admin/Owner CRM | Platform Finance & Commission Settlement Overview | Financial Settlements & Revenue | admin_web_crm_finance_commission_overview | Completed (100%) | Yes (Available in Assets) | Pending Review | Gross platform volume, automated partner commission accruals, escrow balances
ADM-SCR-13 | 4. Admin/Owner CRM | Commission & Revenue Share Rules Configuration | Revenue Configuration Engine | admin_web_crm_commission_configuration | Completed (100%) | Yes (Available in Assets) | Pending Review | Configure platform revenue distribution rules, regional franchise overrides
ADM-SCR-14 | 4. Admin/Owner CRM | Service Catalog & Work-Order Taxonomy | Service Catalog Management | admin_web_crm_service_catalog | Completed (100%) | Yes (Available in Assets) | Pending Review | Standard repair/install procedures, baseline pricing, skill requirements
ADM-SCR-15 | 4. Admin/Owner CRM | Service Category Hierarchy Management | Taxonomy Governance | admin_web_crm_service_category_management | Completed (100%) | Yes (Available in Assets) | Pending Review | Manage electrical classifications, tier hierarchies, safety protocols
ADM-SCR-16 | 4. Admin/Owner CRM | Subscription Modules & Recurring Tier Management | Subscription Engine | admin_web_crm_subscription_modules | Completed (100%) | Yes (Available in Assets) | Pending Review | Protection plans oversight across Consumers (1-Mo) and Partners (3-Mo Free)
ADM-SCR-17 | 4. Admin/Owner CRM | Subscription Dossier — Zex Shield Protection Plan | Subscription Lifecycle | admin_web_crm_subscription_details | Completed (100%) | Yes (Available in Assets) | Pending Review | Detailed view of plan inclusions, subscriber counts, renewal revenues
ADM-SCR-18 | 4. Admin/Owner CRM | Central Support Desk & Omnichannel Ticket Governance | Support Operations Hub | admin_web_crm_support_desk | Completed (100%) | Yes (Available in Assets) | Pending Review | Omnichannel support ticketing across Customers, Technicians, and Partners
ADM-SCR-19 | 4. Admin/Owner CRM | Support Ticket #SUP-1024 — Delay Escalation | Escalation Resolution Workspace | admin_web_crm_support_ticket_details_sup_1024 | Completed (100%) | Yes (Available in Assets) | Pending Review | Cross-party communication timeline, priority reassignment, SLA override
ADM-SCR-20 | 4. Admin/Owner CRM | Platform System Settings & Global Controls | System Configuration | admin_web_crm_system_settings | Completed (100%) | Yes (Available in Assets) | Pending Review | Global platform rules, API keys, SMS templates, server backups
ADM-SCR-21 | 4. Admin/Owner CRM | Super Admin Account & Security Governance | Security & Access Governance | admin_web_crm_profile_settings | Completed (100%) | Yes (Available in Assets) | Pending Review | Hardware-enforced 2FA, session keys, role-gated permission matrices
ADM-SCR-22 | 4. Admin/Owner CRM | Platform Administrative Audit Logs & Immutable Trail | Compliance & Auditing (WORM) | admin_web_crm_audit_logs | Completed (100%) | Yes (Available in Assets) | Pending Review | WORM-compliant tamper-evident event trail of all admin interventions
PTNR-SCR-01 | 3. Partner Web/App | Regional Partner Operational Command Dashboard | Regional Operations Hub | partner_web_crm_dashboard_maharashtra_team | Completed (100%) | Yes (Available in Assets) | Pending Review | Live dispatch telemetry, pending order queues, active capacity in Maharashtra
PTNR-SCR-02 | 3. Partner Web/App | Territory Job Management & Dispatch Console | Job Operations & Dispatch | partner_web_crm_job_management | Completed (100%) | Yes (Available in Assets) | Pending Review | Customer service request roster, technician assignment, status filters
PTNR-SCR-03 | 3. Partner Web/App | Job Details & Work-Order Lifecycle — #J-1001 | Work Order Execution | partner_web_crm_job_details_j_1001 | Completed (100%) | Yes (Available in Assets) | Pending Review | Telemetry, customer site, technician dispatch status, materials billing
PTNR-SCR-04 | 3. Partner Web/App | Escalated Jobs & SLA Breach Management | Critical SLA Resolution | partner_web_crm_escalated_jobs | Completed (100%) | Yes (Available in Assets) | Pending Review | Field dispatches with SLA countdown breaches, unassigned alerts
PTNR-SCR-05 | 3. Partner Web/App | Emergency Technician Reassignment — Job #J-1005 | Emergency Dispatch Console | partner_web_crm_technician_reassignment_j_1005 | Completed (100%) | Yes (Available in Assets) | Pending Review | Urgent proximity reassignment modal filtering certified nearest technicians
PTNR-SCR-06 | 3. Partner Web/App | Manage Regional Fleet & Technician Roster | Fleet Administration | partner_web_crm_manage_technicians | Completed (100%) | Yes (Available in Assets) | Pending Review | Live roster status, capacity, daily assignments, verification credentials
PTNR-SCR-07 | 3. Partner Web/App | Partner Portal: Technician Dossier — Rajesh Kumar | Fleet Personnel Profile | partner_web_crm_technician_profile_rajesh_kumar | Completed (100%) | Yes (Available in Assets) | Pending Review | Regional supervisor view of technician performance and shift schedules
PTNR-SCR-08 | 3. Partner Web/App | Partner Technician Onboarding & KYC Screening | Personnel Onboarding | partner_web_crm_technician_kyc_review | Completed (100%) | Yes (Available in Assets) | Pending Review | Screen regional applicant certifications, government ID, electrical license
PTNR-SCR-09 | 3. Partner Web/App | Pincode Coverage Density & Fleet Capacity Heatmap | Territory Coverage Analysis | partner_web_crm_pincode_coverage_capacity | Completed (100%) | Yes (Available in Assets) | Pending Review | Monitor zone densities, active dispatch capacities, 30-min SLA perimeters
PTNR-SCR-10 | 3. Partner Web/App | Pincode Deep-Dive: 400001 (Colaba, Mumbai Hub) | Hyperlocal Operations Hub | partner_web_crm_pincode_details_400001_colaba | Completed (100%) | Yes (Available in Assets) | Pending Review | Personnel registered for 30-min rapid deployment in Colaba 400001
PTNR-SCR-11 | 3. Partner Web/App | Tax Invoices & Completed Dispatch Billings | Invoicing & Tax Compliance | partner_web_crm_invoices | Completed (100%) | Yes (Available in Assets) | Pending Review | Filter, review, and export GST tax invoices for completed service dispatches
PTNR-SCR-12 | 3. Partner Web/App | Official Tax Invoice Preview — #INV-2026-001 | Invoice Document Generation | partner_web_crm_invoice_preview_inv_2026_001 | Completed (100%) | Yes (Available in Assets) | Pending Review | Print-ready GST tax invoice with CGST/SGST breakdowns and HSN codes
PTNR-SCR-13 | 3. Partner Web/App | Partner Revenue Shares & Regional Payouts | Payout Management | partner_web_crm_finance_payouts | Completed (100%) | Yes (Available in Assets) | Pending Review | Track franchise commission splits, technician disbursement settlements
PTNR-SCR-14 | 3. Partner Web/App | Financial Transactions & Escrow Settlement Ledger | Financial Ledger & Escrow | partner_web_crm_transactions_ledger | Completed (100%) | Yes (Available in Assets) | Pending Review | Immutable financial audit trail of all job billings and bank releases
PTNR-SCR-15 | 3. Partner Web/App | Partner Support Center & Operations Helpdesk | Partner Support Workspace | partner_web_crm_support_center | Completed (100%) | Yes (Available in Assets) | Pending Review | Submit escalation tickets to platform headquarters and track tickets
PTNR-SCR-16 | 3. Partner Web/App | Partner Ticket #SUP-1024: High-Voltage Assignment | Support Case View | partner_web_crm_support_ticket_details_sup_1024 | Completed (100%) | Yes (Available in Assets) | Pending Review | Direct communication thread regarding high-voltage transformer escalation
PTNR-SCR-17 | 3. Partner Web/App | Partner Entity Profile & Operating Settings | Partner Configuration | partner_web_crm_profile_settings | Completed (100%) | Yes (Available in Assets) | Pending Review | Licensed entity corporate profile, banking settlement IFSC details
PTNR-SCR-18 | 3. Partner Web/App | Partner Web CRM — Master Design System Board 1 | Design System & UI Componentry | partner_web_crm_final_design_system_board_1 | Completed (100%) | Yes (Available in Assets) | Pending Review | Component library, color tokens, typography scales, buttons, badges
PTNR-SCR-19 | 3. Partner Web/App | Admin Web CRM — Master Design System Board 2 | Design System & UI Componentry | partner_web_crm_final_design_system_board_2 | Completed (100%) | Yes (Available in Assets) | Pending Review | Master component library, telemetry cards, data grids, modal dialogs

## Bugs & Issues
Issue ID | Date Logged | Module | Screen / Component | Issue Description & Reproduction Steps | Severity | Priority | Reported By | Assigned To | Status | Root Cause / Resolution Notes | Verification Date

## Client Feedback - CR
CR ID | Date Logged | Requestor | Module / Screen | Feedback / Change Request Summary | Business Value & Justification | Impact Analysis (Scope / Architecture) | Effort Est. | Approval Status | Target Phase / Sprint | Sign-Off Signee | Client Meeting Remarks

## Milestones
Milestone ID | Milestone Title | Minimum Target | Recommended Target | Phase | Key Deliverables | Completion & Acceptance Criteria | Status | Planned Sign-Off | Sign-Off Authority
MS-01 | Architecture, DB Schema & Multi-Tenant Auth Engine | Day 2.5 | Day 3.5 | Week 1 | PostgreSQL multi-tenant schema, Prisma models, JWT/RBAC auth engine, seed data | Successful schema migration, seed data for 4 roles, authenticated login returns valid role JWT tokens. | Ready to Start | Day 3.5 | Tech Lead / Architect
MS-02 | Core Dispatch Engine & Third-Party Integrations | Day 5.0 | Day 7.5 | Week 1 | Job state machine, pincode matcher, escrow splits, SMS/OTP, S3 photo bucket, Razorpay webhooks | Mock dispatch triggers auto-assignment to pincode technician, calculates commission, and emits lifecycle events. | Pending Pre-requisite | Day 7.5 | Tech Lead / Architect
MS-03 | Super Admin Web CRM Live Data Wired (22 Screens) | Day 7.5 | Day 9.5 | Week 2 | 22 Admin Web CRM screens functional, telemetry dashboard, partner management, KYC audit console | Super Admin can onboard partner, approve technician KYC, override commission rates, and review audit logs. | Pending Pre-requisite | Day 9.5 | Client Product Owner
MS-04 | Partner Web Operations CRM Fully Functional (19 Screens) | Day 9.5 | Day 11.5 | Week 2 | 19 Partner Web CRM screens functional, dispatch queue, SLA escalations, Colaba heatmap, GST invoices | Partner can view state telemetry, handle job reassignment #J-1005, view Colaba 400001 capacity, print invoice #INV-2026-001. | Pending Pre-requisite | Day 11.5 | Regional Franchise Partner
MS-05 | Customer & Technician Mobile Apps Functional (12 Screens) | Day 12.5 | Day 14.5 | Week 2 | 12 Mobile screens functional: Customer booking/tracking, Technician safety checklist, photo capture, OTP completion | End-to-end phone test: Customer books fan repair -> Tech receives job alert -> Navigates -> Completes safety check -> Customer OTP validates -> Invoice generated. | Pending Pre-requisite | Day 14.5 | QA Lead & Product Owner
MS-06 | GATEWAY 1: Core Platform Functional Delivery (Minimum Target) | Day 14.0 | Day 16.0 | Week 2 / 3 | All 41 Web CRM screens and 12 Mobile screens functionally connected to backend APIs with live data flow | All core happy paths functional end-to-end across Customer, Technician, Partner and Admin roles. | Pending Pre-requisite | Day 16.0 | Executive Product Sponsor
MS-07 | Comprehensive QA, SLA Stress Testing & Defect Remediation | Day 15.0 | Day 19.0 | Week 3 (Buffer) | Zero P0/P1 open bugs, stress testing of SLA countdowns, WORM audit verification, payment reconciliation test | All test cases in QA matrix pass with 100% test run evidence logged. | Pending Pre-requisite | Day 19.0 | QA Lead
MS-08 | Client UAT Demo Walkthrough & Change Feedback Resolution | Day 16.0 | Day 20.0 | Week 3 (Buffer) | Formal client walkthrough across all systems, stakeholder demo, resolution of critical feedback items | Client Product Owner formally signs off UAT acceptance document. | Pending Pre-requisite | Day 20.0 | Client Stakeholder
MS-09 | GATEWAY 2: Production Deployment & Platform Handover (Recommended Target) | Day 16.5 | Day 21.0 | Week 3 (Buffer) | Production cloud provisioning, managed PostgreSQL DB, SSL certificates, custom domains, APK/IPA builds | Platform live in production environment; production credentials and deployment runbook transferred. | Pending Pre-requisite | Day 21.0 | Client Stakeholder & Tech Lead

## Dependencies
Dep ID | Pre-requisite Item / Task | Dependent Item / Task | Dependency Type | Impact Description | Critical Path (Yes/No) | Risk Severity | Mitigation / Contigency Plan
DEP-001 | TASK-001 & TASK-002: DB Schema & Multi-Tenant Migrations | All Backend Services (TASK-003 to TASK-009) | Finish-to-Start (FS) | Database models must be locked and migrated before endpoints can store entity data. | Yes | Critical | Use Prisma ORM with strict TypeScript types to prevent runtime schema mismatches.
DEP-002 | TASK-003: Authentication & RBAC Engine | All Web CRM & Mobile Interfaces (TASK-014 to TASK-042) | Finish-to-Start (FS) | Screens cannot securely query APIs without JWT access tokens and role claims. | Yes | Critical | Build clean mock auth interceptors for isolated UI testing if auth server is undergoing maintenance.
DEP-003 | TASK-007: Job Lifecycle State Machine | TASK-024: Job Management & TASK-033: Booking Flow | Finish-to-Start (FS) | Cannot change job states (Assigned, En Route, Started, Done) without finite state machine logic. | Yes | Critical | Formalize state transitions in a centralized enum with automated transition validator function.
DEP-004 | TASK-010 to TASK-013: Third-Party Integrations | TASK-033 (Payment) & TASK-039 (Photo Capture) | Finish-to-Start (FS) | Live payments, SMS OTP, and photo uploads depend on valid external API credentials. | Yes | High | Client must supply production/sandbox API keys for Razorpay, AWS S3, and SMS provider by Day 1.
DEP-005 | Week 1 & 2: Web CRM Implementation | Week 2 & 3: Mobile App Field Coordination | Finish-to-Start (FS) | Partner and Admin must exist to onboard technicians and review KYC before mobile dispatch can be tested. | Yes | Medium | Solo developer builds Web CRM management first, seeding realistic technician and pincode datasets.
DEP-006 | Week 2: Mobile App Verification Flow | TASK-043: End-to-End System QA Simulation | Finish-to-Start (FS) | End-to-end integration cannot be verified without physical mobile app device flows. | Yes | High | Run QA on physical Android and iOS test devices alongside emulators for camera & GPS validation.
DEP-007 | Week 3 Buffer: QA & Defect Remediation | TASK-045: Production Deployment & Store Release | Finish-to-Start (FS) | Production release cannot proceed with open P0 blockers or unverified payment reconciliations. | Yes | Critical | Week 3 provides the dedicated buffer for client feedback iterations and store build signing.